| Start Date | Action Goals | Responsible Person(s) |
| --- | --- | --- |
| KEY: IMPL = implementation date | Enter IMPL date here: _____________ (use this date to fill in blanks below as appropriate) |  |
| 7 months before IMPL ____________________ | [Integrated Health] briefs Facility Manager on policy and online tool kit | [Integrated Health] |
| 6½ months before IMPL _____________________ | Establish Steering Team Include representatives from 24/7 team, HR, Safety, Security, Hourly and Salaried population | Facility Manager |
| 6 months before IMPL __________________ | Review policy Determine policy implementation date (general recommendation is to begin workplan action goals between 4 to 6 months prior to implementation date) | Facility Manager and Steering Team |
| 5½ months before IMPL __________________ | Review communications (see “Communication Tools” on website) Determine budget Identify structural changes Positioning of smoking areas to meet entrance clearance guidelines Ash and butt container positioning Signage positioning Brainstorm concerns and issues Security Compliance Liabilities | Facility Steering Team |
| 5 months before IMPL __________________ | Brief facility management staff about implementation plan Policy Timeline Procedures Compliance | Facility Steering Team |
| 4 months before IMPL __________________ | Initial facility announcement of new policy using first Key Message (see “Communication Tools” on website) for bulletin boards and/or email from facility management Implement the remaining Key Messages using time frames indicated | Facility Steering Team |
| 3 months before IMPL __________________ | Print FAQs and Policy (see “Communication Tools” on website) to distribute to employees | 24/7 Health & Safety team |
| 3 months before IMPL __________________ | Print and hang “effective Month Day this facility will become a tobacco-free facility” posters (see “Communication Tools” on website) | 24/7 Health & Safety team |
| 2 months before IMPL __________________ | Use next Key Message Use PPT deck (see “Communication Tools” on website) to educate employees at: Communications meetings Department meetings Shift meetings | Facility Steering Team |
| 1 month before IMPL __________________ | Send employee letter (see “Communication Tools” on website) Salaried employees – to company mail stop Hourly – to supervisors for distribution Send letter to contractors and suppliers | Facility Steering Team |
| 1 week before IMPL __________________ | Contact Anne Kenlon in Corporate Communications to feature a SpotLight article (e.g. “Wlilmington goes tobacco-free!”) Communicate the number and the person to call to handle compliance issues or disputes Erect outdoor designated smoking areas | Facility Steering Team |
| The night before IMPL __________________ | “This is now a tobacco-free facility” signage – 11x17 poster, 8½x11 poster, laminated stand-up signs for lobby desk, HR, ER & nurses’ offices | Facility Steering Team |