| Start Date | Action Goals | Responsible Person(s) |
| --- | --- | --- |
| KEY: IMPL = implementation date | Enter IMPL date here: _____________ (use this date to fill in blanks below as appropriate) |  |
| 7 months before IMPL ____________________ | [Integrated Health] briefs Facility Manager on policy and online tool kit | [Integrated Health] |
| 6½ months before IMPL _____________________ | Establish Steering Team Include representatives from 24/7 team, HR, Safety, Security, Hourly and Salaried population | Facility Manager |
| 6 months before IMPL __________________ | Review policy Determine policy implementation date (general recommendation is to begin workplan action goals between 4 to 6 months prior to implementation date) | Facility Manager and Steering Team |
| 5½ months before IMPL __________________ | Review communications (see “Communication Tools” on website) Determine budget Identify any structural changes to remove smoking areas Brainstorm concerns and issues Security Compliance Liabilities Identify potential off-premise locations that might be utilized by employees as alternatives to smoking on the premises. Discuss and address: Safety issues and remediation (i.e. street crossings, road side parking, traffic, fire etc…) Community/Neighbor issues and remediation (i.e. using private and public space alternative to smoke) Break durations and time to travel an off-premise location to smoke | Facility Steering Team |
| 5 months before IMPL __________________ | Brief facility management staff about implementation plan Policy Timeline Procedures Compliance Finalize action plans to address off-premise smoking issue Safety issues Community/Neighbor issues Breaks | Facility Steering Team |
| 4 months before IMPL __________________ | Initial facility announcement of new policy using first Key Message (see “Communication Tools” on website) for bulletin boards and/or email from facility management Implement the remaining Key Messages using time frames indicated | Facility Steering Team |
| 3 months before IMPL __________________ | Print FAQs and Policy (see “Communication Tools” on website) to distribute to employees Add to FAQs information to address employees traveling off-premise to smoke Safety Community/Neighbor Breaks | 24/7 Health & Safety team |
| 3 months before IMPL __________________ | Print and hang “effective Month Day this facility will become a tobacco-free premises” posters (see “Communication Tools” on website) | 24/7 Health & Safety team |
| 2 months before IMPL __________________ | Use next Key Message Use PPT deck (see “Communication Tools” on website) to educate employees at: Communications meetings Department meetings Shift meetings | Facility Steering Team |
| 1 month before IMPL __________________ | Send employee letter (see “Communication Tools” on website) Salaried employees – to company mail stop Hourly – to supervisors for distribution Send letter to contractors and suppliers | Facility Steering Team |
| 1 week before IMPL __________________ | Contact Anne Kenlon in Corporate Communications to feature a SpotLight article (e.g. “Wilmington goes tobacco-free!”) Communicate the number and the person to call to handle compliance issues or disputes Take down smoking areas | Facility Steering Team |
| The night before IMPL __________________ | “This is now a tobacco-free premises” signage – 11x17 poster, 8½x11 poster, laminated stand-up signs for lobby desk, HR, ER & nurses’ offices | Facility Steering Team |